## Agile Backlog 1
Iteration 1 Backlog
Notes Iteration 1, all numbers begin with 101 and continue upward. In Iteration 2, all numbers start with 201 and continue upward. In Iteration 3, all numbers begin with 301 and continue upward. Start number column from 101. Outside requirements such as Inception pieces or other requirements are numbered 1-100. PD = Person Day and the number of hours they will spend on a task. Only high-priority items are prioritized, assigned to iteration, and estimated.
Number | Description | PD est. | By
High Priority (light green)
Iteration 1
101 | Set up user registration module | 4 | Faith Okunola, Shresta Rapol
102 | Design profile creation interface | 3 | Faith Okunola |  | 1 PD = 8 hours
103 | Build AI matchmaking algorithm | 6 | Chiagozie Maduemesi, Shresta Rapol
104 | Create mentor search functionality | 4 | Chiagozie Maduemesi, Onolemen Omokhuale
105 | Backend database setup for users and profiles | 5 | Onolemen Omokhuale, Shresta Rapol
106 | Conduct usability testing for implemented features | 3 | Chiagozie Maduemesi
…
Iteration 2
201 | Develop skill exchange workflow | TBD | TBD
202 | Integrate video conferencing module | TBD | TBD
203 | Implement collaboration request feature | TBD | TBD
Iteration 3
301 | Build task management interface | 5 PD | Faith Okunola, Onolemen Omokhuale
| Medium Priority (light blue) |  |  | Note: assigned medium and low tasks are prioritized but not yet assigned to iteration, nor estimated.
302 | Create advanced reporting and analytics | TBD | TBD
303 | Add additional collaboration tools (e.g., whiteboard) | TBD | TBD
304 | Design branding and UI enhancements | TBD | TBD
Low Priority (pink)
305 | Include optional user onboarding tutorial | TBD | TBD
306 | Optimize backend algorithms for AI matching | TBD | TBD

## Iteration 1 Plan
Iteration Plan 1
Project | Co-Lab Connect
Team Names: | Chiagozie Maduemesi, Faith Okunola, Onolemen Omokhuale, Shresta Rapol
Team Number: | Group-8
1. What deliverables did the team plan to complete by the end of the iteration? Refer to your Project Plan submitted in Week 3 to determine which items should be completed. Please note that dates may change as the Iterations continue and various issues arise. Did this Iteration include other work items such as setting up a development environment or bug fixes in the Iteration backlog list?
Number | Description | Responsibility (Initials) | Project Plan adherence?
101 | Set up user registration module | FO, SR | Yes
102 | Design profile creation interface | FO | Yes
103 | Build AI matchmaking algorithm | CM, SR | Yes
104 | Create mentor search functionality | CM, OO | Yes
105 | Backend database setup for users and profiles | OO, SR | Yes
106 | Conduct usability testing for implemented features | CM | Yes
2. Did the team identify the architecture (hardware/software/platform/solution design) early? Was there a architecture owner assigned?
List of architecture being used | Concerns (current and potential) | Owner Assigned (Initials)
Frontend: React.js | Potential scalability and styling consistency issues. | FO
Backend: Node.js with Express.js | API response time optimization. | CM
Database: MongoDB | Managing large-scale queries and maintaining data integrity. | OO
AI Matching: TensorFlow.js | Accuracy of matchmaking results; optimization for faster execution. | SR
Collaboration Tools: WebRTC (for video) | Compatibility across different browsers. | SR
3. Did your team visually track your progress by using tools such as Microsoft Project, SharePoint, Trello, etc.? Explain why you choose this tool.
Tracking Software Used | Why?
GitHub | Version control and collaboration on codebase, tracking commits.
Microsoft Teams | Efficient communication and task updates during daily stand-ups.
The point of the Iteration Plan is to have a goal set from the backlog. Iteration Plan and backlog are submitted prior to each iteration. Iteration Plans can repeat work items if feedback is provided by the client that further updates are required for a deliverable. Each iteration should have a working code demostration.
Note: These guiding questions are not meant to be exhaustive. Each team is responsible for the delivery of a workable solution.

## Agile Release Summary 1
Iteration 1: Release Plan Summary
Note The top row lists Number, Feature/Requirement, Inception, Iterations 1, 2, and 3, and Transition. The Number and Feature/Requirements column information is provided in your backlog. The numbers and task must match the backlog information. Once this information is inputted into your release summary chart your team will determine what iteration the tasks will be completed and how many hours are needed to complete each task. Each group should expect to work 9 person-days (PD) per week. A reminder that 1 person day is equal to 4 person hours.
Colour Coding
Inception and Other Requirements (gray) | Iteration 1 (orange) | Iteration 2 (light Blue) | Iteration 3 (light yellow) | Transition (light green)
Number | Feature / Requirement | Inception PD | Iteration #1 PD | Iteration #2 PD | Iteration #3 PD | Transition PD
|  | Due: | Due: | Due: | Due: | Due:
101 | Set up user registration module | 0 | 4 | 0 | 0 | 0
102 | Design profile creation interface | 0 | 3 | 0 | 0 | 0
103 | Build AI matchmaking algorithm | 0 | 6 | 0 | 0 | 0
104 | Create mentor search functionality | 0 | 4 | 0 | 0 | 0
105 | Backend database setup for profiles | 0 | 5 | 0 | 0 | 0
201 | Develop skill exchange workflow | 0 | 0 | 6 | 0 | 0
202 | Integrate video conferencing module | 0 | 0 | 5 | 0 | 0
301 | Build task management interface | 0 | 0 | 0 | 5 | 0
302 | Create advanced reporting and analytics | 0 | 0 | 0 | 4 | 0
303 | Add additional collaboration tools | 0 | 0 | 0 | 3 | 0
Work Effort in Person Days (PD) 1 PD hour equals 4 hours |  | 0 | 88 | 44 | 48 | 0
Total Project Hours |  | 180

## Agile Backlog 2
Iteration 2 Backlog
Notes Iteration 1, all numbers begin with 101 and continue upward. In Iteration 2, all numbers start with 201 and continue upward. In Iteration 3, all numbers begin with 301 and continue upward. Start number column from 201. Outside requirements such as Inception pieces or other requirements are numbered 1-100. PD = Person Day and the number of hours they will spend on a task. Only high-priority items are prioritized, assigned to iteration, and estimated.
Number | Description | PD est. | By
High Priority
Iteration 1
Iteration 2
201 | Develop skill exchange workflow | 6 PD | Faith Okunola, Shresta Rapol
202 | Integrate video conferencing module | 5 PD | Chiagozie Maduemesi, Onolemen Omokhuale
203 | Implement collaboration request feature | 4 PD | Faith Okunola, Shresta Rapol
Iteration 3
301 | Build task management interface | 5 PD | Faith Okunola, Onolemen Omokhuale
302 | Create advanced reporting and analytics | 4 PD | TBD
303 | Add additional collaboration tools (e.g., whiteboard) | 3 PD | TBD
Medium Priority
304 | Design branding and UI enhancements | TBD | TBD
305 | Include optional user onboarding tutorial | TBD | TBD
Low Priority
306 | Optimize backend algorithms for AI matching | TBD | TBD

## Iteration 2 Plan
Iteration Plan 2
Project | Co-Lab Connect
Team Names: | Chiagozie Maduemesi, Faith Okunola, Onolemen Omokhuale, Shresta Rapol
Team Number: | Group-8
1. What deliverables did the team plan to complete by the end of the iteration? Refer to your Project Plan submitted in Week 3 to determine which items should be completed. Please note that dates may change as the Iterations continue and various issues arise. Did this Iteration include other work items such as setting up a development environment or bug fixes in the Iteration backlog list?
Number | Description | Responsibility (Initials) | Project Plan adherence?
201 | Develop skill exchange workflow | Faith Okunola, Shresta Rapol | Yes
202 | Integrate video conferencing module | Chiagozie Maduemesi, Onolemen Omokhuale | Yes
203 | Implement collaboration request feature | Faith Okunola, Shresta Rapol | Yes
301 | Build task management interface | Faith Okunola, Onolemen Omokhuale | Yes
302 | Create advanced reporting and analytics | TBD | No (Pending dependencies)
303 | Add additional collaboration tools (e.g., whiteboard) | TBD | No
2. Did the team identify the architecture (hardware/software/platform/solution design) early? Was there a architecture owner assigned?
List of architecture being used | Concerns (current and potential) | Owner Assigned (Initials)
Frontend: React.js | Potential for scalability and maintenance of large UI components. | Faith Okunola
Backend: Node.js with Express.js | API performance during high traffic. | Chiagozie Maduemesi
Database: MongoDB | Managing complex relationships in a NoSQL structure. | Onolemen Omokhuale
AI Matching: TensorFlow.js | Efficiency of the AI algorithm for real-time matchmaking. | Shresta Rapol
Collaboration Tools: WebRTC (video calls) | Browser compatibility and latency in video calls. | Shresta Rapol
3. Is your team still using the tracking software for your project? Are there any significant timeline changes to your project?
Tracking Software | Progress & Updates
GitHub | Version control and collaboration on the codebase.
Microsoft Teams | Used for daily stand-ups and overall communication.
The point of the Iteration Plan is to have a goal set from the backlog. Iteration Plan and backlog are submitted prior to each iteration. Iteration Plans can repeat work items if feedback is provided by the client that further updates are required for a deliverable. Each iteration should have a working code demostration.
Note: These guiding questions are not meant to be exhaustive. Each team is responsible for the delivery of a workable solution.

## Agile Release Summary 2
Iteration 2: Release Plan Summary
Note The top row lists Number, Feature/Requirement, Inception, Iterations 1, 2, and 3, and Transition. The Number and Feature/Requirements column information is provided in your backlog. The numbers and tasks must match the backlog information. Once this information is inputted into your release summary chart your team will determine what iteration the tasks will be completed and how many hours are needed to complete each task. Each group should expect to work 9 person-days (PD) per week. A reminder that 1 person day is equal to 4 person hours.
Colour Coding
Inception and Other Requirements (gray) | Iteration 1 (orange) | Iteration 2 (light Blue) | Iteration 3 (light yellow) | Transition (light green)
Number | Feature / Requirement | Inception | Iteration #1 | Iteration #2 | Iteration #3 | Transition
|  | Due: | Due: | Due: | Due: | Due:
101 | Set up user registration module | 0 | 4 | 0 | 0 | 0
102 | Design profile creation interface | 0 | 3 | 0 | 0 | 0
103 | Build AI matchmaking algorithm | 0 | 6 | 0 | 0 | 0
104 | Create mentor search functionality | 0 | 4 | 0 | 0 | 0
105 | Backend database setup for profiles | 0 | 5 | 0 | 0 | 0
201 | Develop skill exchange workflow | 0 | 0 | 6 | 0 | 0
202 | Integrate video conferencing module | 0 | 0 | 5 | 0 | 0
301 | Build task management interface | 0 | 0 | 0 | 5 | 0
302 | Create advanced reporting and analytics | 0 | 0 | 0 | 4 | 0
303 | Add additional collaboration tools | 0 | 0 | 0 | 3 | 0
Work Effort in Person Days (PD) 1 PD hour equals 4 hours |  | 0 | 88 | 44 | 48 | 0
Total Project Hours |  | 180

## Agile Backlog 3
Iteration 3 Backlog
Notes Iteration 1, all numbers begin with 101 and continue upward. In Iteration 2, all numbers start with 201 and continue upward. In Iteration 3, all numbers begin with 301 and continue upward. Start number column from 201. Outside requirements such as Inception pieces or other requirements are numbered 1-100. PD = Person Day and the number of hours they will spend on a task. Only high-priority items are prioritized, assigned to iteration, and estimated.
Number | Description | PD est. | By
High Priority
Iteration 1
Iteration 2
Iteration 3
301 | Build task management interface | 5 PD | Faith Okunola, Onolemen Omokhuale
302 | Create advanced reporting and analytics | 4 PD | Chiagozie Maduemesi, Shresta Rapol
303 | Add additional collaboration tools (e.g., whiteboard) | 3 PD | Faith Okunola, Shresta Rapol
Medium Priority
304 | Design branding and UI enhancements | 4 PD | Faith Okunola, Shresta Rapol
305 | Include optional user onboarding tutorial | 3 PD | Chiagozie Maduemesi, Onolemen Omokhuale
Low Priority
306 | Optimize backend algorithms for AI matching | 4 PD | Chiagozie Maduemesi, Onolemen Omokhuale

## Iteration 3 Plan
Iteration Plan 3
Project | Co-Lab Connect
Team Names: | Chiagozie Maduemesi, Faith Okunola, Onolemen Omokhuale, Shresta Rapol
Team Number: | Group-8
1. What deliverables did the team plan to complete by the end of the iteration? Refer to your Project Plan submitted in Week 3 to determine which items should be completed. Please note that dates may change as the Iterations continue and various issues arise. Did this Iteration include other work items such as setting up a development environment or bug fixes in the Iteration backlog list?
Number | Description | Responsibility (Initials) | Project Plan adherence?
301 | Build task management interface | Faith Okunola, Onolemen Omokhuale | Yes
302 | Create advanced reporting and analytics | Chiagozie Maduemesi, Shresta Rapol | Yes
303 | Add additional collaboration tools (e.g., whiteboard) | Faith Okunola, Shresta Rapol | Yes
304 | Design branding and UI enhancements | Faith Okunola, Shresta Rapol | Yes
305 | Include optional user onboarding tutorial | Chiagozie Maduemesi, Onolemen Omokhuale | Yes
306 | Optimize backend algorithms for AI matching | Chiagozie Maduemesi, Onolemen Omokhuale | Yes
2. Did the team identify the architecture (hardware/software/platform/solution design) early? Was there a architecture owner assigned?
List of architecture being used | Concerns (current and potential) | Owner Assigned (Initials)
Frontend: React.js | Potential for scalability and maintenance of large UI components. | Faith Okunola
Backend: Node.js with Express.js | API performance during high traffic. | Chiagozie Maduemesi
Database: MongoDB | Managing complex relationships in a NoSQL structure. | Onolemen Omokhuale
AI Matching: TensorFlow.js | Efficiency of the AI algorithm for real-time matchmaking. | Shresta Rapol
Collaboration Tools: WebRTC (video calls) | Browser compatibility and latency in video calls. | Shresta Rapol
3. Is your team still using the tracking software for your project? Are there any significant timeline changes to your project?
Tracking Software | Progress & Updates
GitHub | Version control and collaboration on the codebase.
Microsoft Teams | Used for daily stand-ups and overall communication.
The point of the Iteration Plan is to have a goal set from the backlog. Iteration Plan and backlog are submitted prior to each iteration. Iteration Plans can repeat work items if feedback is provided by the client that further updates are required for a deliverable. Each iteration should have a working code demostration.
Note: These guiding questions are not meant to be exhaustive. Each team is responsible for the delivery of a workable solution.

## Agile Release Summary 3
Iteration 3: Release Plan Summary
Note The top row lists Number, Feature/Requirement, Inception, Iterations 1, 2, and 3, and Transition. The Number and Feature/Requirements column information is provided in your backlog. The numbers and task must match the backlog information. Once this information is inputted into your release summary chart your team will determine what iteration the tasks will be completed and how many hours are needed to complete each task. Each group should expect to work 9 person-days (PD) per week. A reminder that 1 person day is equal to 4 person hours.
Colour Coding
Inception and Other Requirements (gray) | Iteration 1 (orange) | Iteration 2 (light Blue) | Iteration 3 (light yellow) | Transition (light green)
Number | Feature / Requirement | Inception | Iteration #1 | Iteration #2 | Iteration #3 | Transition
|  | Due: | Due: | Due: | Due: | Due:
101 | Set up user registration module | 0 | 1 | 0 | 0 | 0
102 | Design profile creation interface | 0 | 1 | 0 | 0 | 0
103 | Build AI matchmaking algorithm | 0 | 2 | 0 | 0 | 0
104 | Create mentor search functionality | 0 | 1 | 0 | 0 | 0
105 | Backend database setup for profiles | 0 | 1.5 | 0 | 0 | 0
201 | Develop skill exchange workflow | 0 | 0 | 1.5 | 0 | 0
202 | Integrate video conferencing module | 0 | 0 | 1.25 | 0 | 0
301 | Build task management interface | 0 | 0 | 0 | 1.25 | 0
302 | Create advanced reporting and analytics | 0 | 0 | 0 | 1 | 0
303 | Add additional collaboration tools | 0 | 0 | 0 | 0.75 | 0
304 | Design branding and UI enhancements | 0 | 0 | 0 | 1 | 0
305 | Include optional user onboarding tutorial | 0 | 0 | 0 | 1 | 0
306 | Optimize backend algorithms for AI matching | 0 | 0 | 0 | 1.5 | 0
Work Effort in Person Days (PD) 1 PD hour equals 4 hours |  | 0 | 26 | 11 | 26 | 0
Total Project Hours |  | 63